# November activities

1.Logos will be designed in each school using different techniques and  the  one  logo will be chosen for each country.

The  5 logos will be posted online on the 15th of November and they will be  voted  to choose a logo for the project, by November 20th.

(I can’t remember the way they will vote – Google form ?)

(I think it will be easier to choose only from 5 logos and not from 15 , as we spoke during the mmeting)

2.PRESENTATION OF EACH COUNTRY – using ISSU or ppt or other app . They will be uploaded on the website .

# December activities

1.Pupils will access the information about their partners.

2.E-twinning accounts for 50 or 100 pupils from each school created by coordinators

3.Each country presents 3 games .

# January  activities

1.Erasmus Games Event- pupils in each school will play the games of their partners. ( 27th-31st January)

2.Online Live Competition- using KAHOOT  ( 27th-31st January)

# DATES OF THE LTT ACTIVITIES:

Each coordinator will check with the headmasters and will confirm the dates:

- ROMANIA- 26-29 NOVEMBER  2019

- AUSTRIA – 17-20 MARCH 2020

- GREECE (PUPILS) – 13-16 OCTOBER 2020

- ITALY – 16-19 MARCH 2021

- CYPRUS (PUPILS)  – 25-28 MAY 2021

** 2ND  TRANSNATIONL MEETING – AUSTRIA – 20-21 APRIL 2021

# APPS WE’VE DISCUSSED:

We’ve decided to use :

KAHOOT / EDUCA – ONLINE GAMES COMPETITION ( 10 questions for each country – 50 questions in total)

ZOOM-ONLINE COFERENCE

GOOGLE FORMS – EVALUATING

ANSWER GARDEN- EVALUATING  THE PROJECT + THE FAVOURITE HERO

Each coordinator will use the app that best fits :

ISSU- PRESENTATIONS

COMPHONE

PPT- MP4

VOKI- presenting heroes – we’ll exchange the VOKIS created by pupils , they will access them on PADLET and will use ANSWER GARDEN to vote the favourite hero

CALAMEO

STORYJUMPER

LINOIT

PADLET

KIZOA – VIDEO MAKER

VIDEOSHOW

QUIK – VIDEO SHOW