|  | Name of the project: GAMES FOR ACTIVE LEARNING - 2019-1-RO01-A229-063665 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | PROJECT TIMETABLE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 |  | M21 | M22 | M23 | M24 |
|  | Project activity* |  | sep | oct | nov | dec | jan | feb | mar | apr | may | june | july | aug | sep | oct | nov | dec | jan | feb | mar | apr |  | may | june | aug | sep |
|  | A1 |  | A1 |  | A1 | A1 |  |  |  | A1 |  |  |  |  | A1 |  |  | A1 | A1 |  | A1 | A1 |  | A1 | A1 | A1 | A1 |
|  | A2 |  |  | A2 | A2 |  |  | A2 |  | A2 |  |  |  |  | A2 |  |  |  |  |  | A2 |  |  | A2 |  |  |  |
|  | A3 |  | A3 | A3 | A3 | A3 | A3 | A3 | A3 | A3 | A3 | A3 |  |  | A3 | A3 | A3 | A3 | A3 | A3 | A3 | A3 |  | A3 | A3 | A3 | A3 |
|  | A4 |  | A4 | A4 |  |  |  |  |  |  |  | A4 |  |  | A4 | A4 |  |  |  |  |  |  |  | A4 | A4 |  |  |
|  | A5 |  |  | A5 | A5 | A5 | A5 | A5 | A5 | A5 | A5 |  |  |  | A5 | A5 | A5 | A5 | A5 | A5 | A5 | A5 |  | A5 | A5 |  |  |
|  | A6 |  |  | A6 |  |  | A6 |  |  | A6 | A6 |  |  |  | A6 |  |  | A6 |  | A6 |  | A6 |  | A6 |  |  |  |
|  | A7 |  | A7 | A7 |  | A7 |  |  |  | A7 | A7 |  |  |  | A7 |  |  | A7 |  | A7 | A7 |  |  | A7 | A7 | A7 | A7 |
|  | A8 |  |  |  | A8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A8 | A8 |  | A8 |  |  |  |
|  | M1 |  |  | M1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | M2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M2 |  |  |  |  |  |
|  | C1 |  |  |  | C1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | C2 |  |  |  |  |  |  |  |  | C2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | C3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C3 |  |  |  |  |  |  |  |  |  |  |  |
|  | C4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C4 |  |  | C5 |  |  |  |

|  | *Project activity types: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A1- ADMINISTRATIVE ARANGEMENTS |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | An | - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A2- CULTURAL PREPARATION |  |  |  |  |  |  |  |  |  |  |
|  |  | On/An | - INTELLECTUAL OUTPUTS/ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A3- Technical Preparation/ Implementation ICT tools : website, E-Twinning, Social network |  |  |  |  |  |  |  |  |  |  |
|  |  | Mn | - TRANSNATIONAL PROJECT MEETINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A4- Expert support for the creation of the Web page of the project |  |  |  |  |  |  |  |  |  |  |
|  |  | En | - MULTIPLIER EVENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A5- Preparation and implementation of the activities of the project |  |  |  |  |  |  |  |  |  |  |
|  |  | Cn | - LEARNING/TEACHING/TRAINING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A6- Monitoring-evaluating-Assesement |  |  |  |  |  |  |  |  |  |  |
|  |  | n | - number of the activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A7- Dissemination |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A8- Creation, publishing, editing |  |  |  |  |  |  |  |  |  |  |
|  | Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |