## WORKPLAN
Name of the project: MYSTY
A Project Management and Implementation | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 |  | ALLOCATION OF WORKING DAYS AND OTHER PROJECT COSTS
A1 Coordinate and monitor project activity through work output leaders (incl financial mgmt) | M5: Virtual; M10: Virtual; M16: Virtual; M22: Virtual
A2 Setup project administration process and files required for project coordination | [25 empty] | UOG - UK |  | GRAZ - AT |  | CESIE - IT |  | RFP - HU |  | Sch - UK |  | Sch - AT |  | Sch - IT |  | Sch/Oth - HU | bar: M1 to M2
A3 Setup internal communication systems and project website | [25 empty] | Academic | Other | Academic | Other | Academic | Other | Academic | Other | Academic | Other | Academic | Other | Academic | Other | Academic | Other | bar: M1 to M2
A4 Small scale dissemination activities | [26 empty] | 12000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000 |  | 6000
A5 Liaise with managing authority and report to deadlines, including project closure
O1 MYSTY Learning Materials for Teachers | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
O1-A1 Assessment of current cultural awareness activities in each school | [24 empty] | Each school assesses the current cultural awareness activities in their own school and prepares short report | 1 | 0 | 1 |  | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Nov
O1-A2 Assessment of national curriculum on cultural awareness | [24 empty] | Each country pairing assesses cultural awareness in their national curriculum and prepares short report | 2 | 0 | 2 |  | 2 |  | 2 |  | 8 |  | 8 |  | 8 |  | 8 | bar: Nov
O1-A3 Develop content on how to embed digital storytelling to enhance cultural activities | [24 empty] | Partners develop materials on how to embed the MYSTY Toolbox in their own and different school settings in each country | 2 | 0 | 2 |  | 2 |  | 2 |  | 3 |  | 3 |  | 3 |  | 3 | bar: Dec to Mar
O1-A4 Deliver and capture media training to 16 teachers in partner schools and to non-school partners | [24 empty] | UOG provides online training to 4 teachers from each school and to each non-school partner, and captures training as resource to add to MYSTY Toolbox | 2 | 10 | 2 |  | 2 |  | 2 |  | 4 |  | 4 |  | 4 |  | 4 | bar: Apr
O1-A5 Translate learning materials into all languages of the consortium | [24 empty] | Partners translate learning materials to their own language | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 |  | 0 |  | 0 |  | 0 | bar: May
O1-A6 Upload learning materials to MYSTY Digital Storytelling Toolbox website | [24 empty] | Learning materials and online training recording uploaded to the MYSTY project website by UOG | 0 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | bar: May
O1-A7 Develop research paper arguing permanence (in the form of family food, festival) is what offers security in the face of transience | [24 empty] | Write paper (HEIs) with support from all partners | 20 | 0 | 20 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Apr to Sep
O2 MYSTY Digital Storymaking Guide for Pupils | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
O2-A1 Develop pupil briefings | [24 empty] | Partners discuss content and approach and develop a briefing for teachers to give to their pupils - at same time as O3-A1 | 1 |  | 1 |  | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 | bar: May to Jun
O2-A2 Teachers give school pupil briefings on process | [24 empty] | Teacher in each school gives the briefing to pupils (age group 12-15) - at same time as O3-A2 | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | bar: Jun
O2-A3 Audit the range of digital tools for media collection (partners and pupils) | [24 empty] | Partners and pupils gather information on digital tools available covering a wide and diverse selection | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Jun
O2-A4 Oversee pupils creation of user guide content | [24 empty] | Teachers oversee the creation of the user guide content (covering available tools and how to use them) by pupils | 0 |  | 0 |  | 0 |  | 0 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Jul
O1-A5 Selection and editing of user guide content and translate to English | [24 empty] | Partners select and edit the gathered content to be used in the Guide and translate to English | 1 |  | 5 |  | 5 |  | 5 |  | 1 |  | 1 |  | 1 |  | 1 | bar: Jul to Aug
O1-A6 Comile user guide | [24 empty] | UOG puts the user guide together prior to translation | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | bar: Aug
O2-A7 Translate user guide into all languages of the consortium | [24 empty] | One partner from each country translates the Guide into their own language | 0 |  | 2 |  | 2 |  | 2 |  | 0 |  | 0 |  | 0 |  | 0 | bar: Aug to Sep
O1-A8 Upload user guide to MYSTY Digital Storytelling Toolbox website | [24 empty] | Finalised Guide uploaded to the MYSTY project website by UOG | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | bar: Apr to May
O3 MYSTY Themed Digital Stories Collection | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
O3-A1 Develop pupil briefings (based on experience of UOG's My Jewish Story project) | [24 empty] | Partners discuss content and approach and develop a briefing for teachers to give to their pupils | 10 | 0 | 10 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | bar: May to Jun
O3-A2 Teachers give school pupil briefings on process | [24 empty] | Teacher in each school gives the briefing to pupils (age group 12-15) | 0 | 0 | 0 |  | 0 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Jul
O3-A3 Oversee pupils collection of over 60 stories on family, food, festivals | [24 empty] | Teachers oversee pupils collection of digital stories (approx 15 stories per school, 60 in total) using Guide O2 | 0 | 0 | 0 |  | 0 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | bar: Sep to Nov
O3-A4 Oversee selection and editing of stories for the collection (using O2 Guide) | [24 empty] | Teachers oversee the selection and editing of stories by pupils using the Guide developed in O2 | 2 | 0 | 2 |  | 2 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | bar: Dec
O3-A4 Non-school partners collect and produce their own digital story (12 in total) | [24 empty] | Non-school partners also collect their own digital stories (3 per partner) for teacher sto use in class settings | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 0 |  | 0 |  | 0 |  | 0 | bar: Oct to Dec
O3-A5 Post-production to ensure technical compatability of media files | [24 empty] | UOG works on all digital stories to ensure consistency and compatability of media files | 5 | 0 | 0 |  | 0 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 | bar: Dec to Feb
O3-A6 Translate and subtitle all digital stories to English | [24 empty] | One partner from each country translates their stories into English, and subtitles are added in each language | 0 | 0 | 5 |  | 5 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 | bar: Mar to Apr
O3-A7 Upload digital stories to MYSTY Digital Storytelling Toolbox website | [24 empty] | All stories are uploaded to the MYSTY project website by each school using the Guide developed in O2 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | bar: Apr to May
M Transnational Project Meetings | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
M1 Transnational Project Meeting in UK | [24 empty] | Meeting in UK for 2 people to kick of project |  | 0 |  | 1150 |  | 1150 |  | 1150 |  | 0 |  | 1150 |  | 1150 |  | 1150 | bar: M2
M2 Transnational Project Meeting in Austria | [24 empty] | Meeting in Austria for 2 people to coincide with end of O1 and start of O2 |  | 1725 |  | 0 |  | 1150 |  | 1150 |  | 1150 |  | 0 |  | 1150 |  | 1150 | bar: M7
M3 Transnational Project Meeting in Italy | [24 empty] | Meeting in Italy for 2 people to coincide with end of O2 |  | 1725 |  | 1150 |  | 0 |  | 1150 |  | 1150 |  | 1150 |  | 0 |  | 1150 | bar: M12
M4 Transnational Project Meeting in Hungary | [24 empty] | Meeting in Hungary to close project |  | 1725 |  | 1150 |  | 1150 |  | 0 |  | 1150 |  | 1150 |  | 1150 |  | 0 | bar: M20
E Multiplier Events | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
E1 Two dissemination Workshop (UK) | M19: 50; HU M23: 50 | Two dissemination events, one hosted by School partner and one hosted by non-school partner |  | 5000 |  | 0 |  | 0 |  | 0 |  | 5000 |  | 0 |  | 0 |  | 0
E2 Practice Resource Dissemination Workshop (AT) | M19: 40; HU M23: 40 | Two dissemination events, one hosted by School partner and one hosted by non-school partner |  | 0 |  | 4000 |  | 0 |  | 0 |  | 0 |  | 4000 |  | 0 |  | 0
E3 Practice Resource Dissemination Workshop (IT) | M19: 35; HU M23: 35 | Two dissemination events, one hosted by School partner and one hosted by non-school partner |  | 0 |  | 0 |  | 3500 |  | 0 |  | 0 |  | 0 |  | 3500 |  | 0
E4 Practice Resource Dissemination Workshop (HU) | M19: 20; HU M23: 20 | Two dissemination events, one hosted by School partner and one hosted by non-school partner |  | 0 |  | 0 |  | 0 |  | 2000 |  | 0 |  | 0 |  | 0 |  | 2000
Exceptional Items
Cost of External Evaluation | [26 empty] | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Cost of Translation/Subtitling | [26 empty] | 0 |  | 3000 |  | 3000 |  | 3000 |  | 0 |  | 0 |  | 0 |  | 0
| HU M24: Rate |  | 214 | 162 | 214 | 162 | 214 | 162 | 74 | 55 | 214 | 162 | 214 | 162 | 214 | 162 | 74 | 55
| HU M24: Days |  | 55 | 16 | 60 | 1 | 37 | 1 | 42 | 1 | 38 | 0 | 38 | 0 | 38 | 0 | 38 | 0
| HU M24: Costs |  | 11770 | 2592 | 12840 | 162 | 7918 | 162 | 3108 | 55 | 8132 | 0 | 8132 | 0 | 8132 | 0 | 2812 | 0
| HU M24: Total |  |  | 41537 |  | 29452 |  | 24030 |  | 17613 |  | 22582 |  | 21582 |  | 21082 |  | 14262 | 192140
[26 empty] | UOG - UK |  | GRAZ - AT |  | CESIE - IT |  | RFP - HU |  | Sch - UK |  | Sch - AT |  | Sch - IT |  | Sch/Oth - HU
Note on B17: CAPIE, Gideon: is this output required before IO1 can start?